## Ark1
LOFTHUS PROJECT		DAYS >

ACTIVITY	DONE BY	START	END	1	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25
Meeting with Lofthus	Everybody	1	1
Taking pictures for webpage	Photographer	2	2
Collecting information for web content	Text editor	3	3
Creating text content for webpage	Text editor	3	4
Collecting copywrite information	Copywriter	3	3
Copywriting	Copywriter	3	4
Skeching/designing templates	Web Designer/FE developer	3	7
Meeting with Lofthus for presenting templates	Web Designer/FE developer	8	8
Html	FE Developer	9	11
Css / javascript	FE Developer	12	14
Adding contend to pages	Web Designer/FE developer	14	17
Presenting beta version	Web Designer/FE developer	18	18
Test phase	FE Developer	20	22
Fixing bugs	FE Developer	22	23
Test again	FE Developer	23	24
Product delivery	Web Designer/FE developer	25	25
publishing	FE Developer	25	25